## Proposal: Contoso HR Agent in Microsoft Teams

### Overview

We propose building a flexible, low-code HR agent in Microsoft Teams to serve Contoso’s 200 employees. The agent will handle policy FAQs (Retrieval-Augmented Generation) and end-to-end leave requests via Workday.

### Architecture & Components

- Knowledge Indexing: Azure AI Search S1 with SharePoint in Microsoft 365 indexer for HR policy libraries, including skillset for text extraction and metadata mapping.

- Generative Layer: Azure OpenAI Service for grounding and generation (chat) with prompt templates and citation-aware responses.

- Agent Platform: Microsoft Copilot Studio for agent design, low-code data connections, and Teams deployment.

- Workday Integration: Power Automate flow with premium connector or HTTP actions to Workday leave-management APIs (create/modify/cancel).

- Deployment: Publish Copilot Studio agent into Teams HR app section, accessible to 200 users.

### Licensing & Cost Estimate (Annual)

| Power Automate premium license (service account) | $480/mo × 12 = $5,760 |
| --- | --- |
| Azure AI Search (S1) | $200/mo × 12 = $2,400 |
| Azure OpenAI Service consumption | ~$4,000 |
| Copilot Studio | No additional cost (M365 E3/E5 covered) |
| Development (developer + consultant) | ~$8,000 |
| Total | $20,160 |

### Timeline

- Month 1: Requirements & design, provision Azure Search, configure indexer.

- Month 2: Build Copilot Studio agent, integrate Workday via Power Automate; initial QA.

- Month 3: User acceptance, performance tuning, Teams deployment & training.

### Comparison to Past Projects

- HR Self-Service Bot (2024): 2 months, $18K, RAG FAQ + ServiceNow integration.

- IT Helpdesk Agent (2024): 3 months, $25K, multi-integration; included three change requests.

### Risks & Mitigations

- Scope Creep: Contoso’s history suggests mid-project feature requests—address via clear backlog & change-control process.

- Integration Complexity: Early API sandbox testing and robust logging in Power Automate flows.

- Performance: Scale Azure Search replicas if latency issues arise; monitor OpenAI usage.

### Next Steps

- Approve project scope & budget.

- Provision required Azure & Power Automate licenses.

- Kick off project with detailed requirements workshop.

Prepared by: [Your Name], AI Project Scoping Consultant
Date: June 14, 2026